## Defect_Report
Project Name - Tutorlink
Created By - Tishany.T
Created date - 25 December 2025
Defect ID | Related Test Case ID | Module | Defect Title | Defect Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Reported By | Reported Date | Remarks
DEF_01 | TC_ST_05 | Student Login | Error message not displayed for invalid login | System does not display error message when invalid credentials are entered | 1. Open login page 2. Enter invalid credentials 3. Click Login | Error message should be displayed | No error message shown | Medium | High | Closed | Tishany .T | 24-Dec-2025 | Fixed after validation handling
DEF_02 | TC_ST_12 | Tutor Request | Request submitted without validation | Tutor request form allows submission with empty fields | 1. Login as student 2. Open request form 3. Submit with empty fields | Validation message should appear | Request submitted without validation | High | High | Closed | Tishany .T | 24-Dec-2025 | Validation logic implemented
DEF_03 | TC_ST_16 | Student Profile | Profile image not uploading | Profile image upload fails when Firebase Cloud Storage is not enabled | 1. Login as student 2. Navigate to Profile page 3. Upload image 4. Save | Profile image should upload successfully | Image upload failed | Medium | Medium | Closed | Tishany .T | 25-Dec-2025 | Resolved by enabling Firebase Cloud Storage
DEF_04 | TC_ST_07 | Student Dashboard | Dashboard content not updating dynamically | Dashboard does not refresh automatically when data changes | 1. Login as student 2. Update underlying data 3. Observe dashboard | Dashboard should update in real time | Dashboard updates only after refresh | Medium | Medium | Closed | Tishany .T | 25-Dec-2025 | Resolved by adding Firebase real-time listeners